## Sheet1
TEST CASES FOR NCC-CLOUDSTACK INTEGRATION
Ref # | Test Description | Variants | Expected Result
Install and Set up - Autoprovisioning
1 | Install and configure NCC |  | NCC should be reachable to Cloudstack
2 | Register Cloudstack Admin keys with NCC by creating an account with NCC |  | Cloudstack account should be able to perform Admin operations in Cloudstack through NCC
3 | Upload VPX image on NCC |  | Image available on Cloudstack
4 | Create different Service Packages | VPX vs SDX vs MPX Shared vs Dedicated Different Licenses (NCC) | 1. Service Package should be available and registered in NCC 2. listNetscalerServicePackage should list the service packages available
5 | Template register |  | Image should be downloadable VPX template should get registered by NCC on Cloudstack using registerTemplate API
6 | Register NCC using registerNetscalerControlCenterAPI Provide IP, account details |  | NCC should get registered with Cloudstack listNetscalerControlCenter should list the NCC details
7 | Try to register one more NCC |  | Should fail - only one NCC will manage a Cloudstack installation Verify Event is not generated
8 | Delete a configured NCC using deleteNetscalerControlCenter |  | If no NS are tied to the NCC which are in use then we should be able to delete the NCC. Otherwise it should throw appropriate error messages Post deletion, all service packages should be deleted
9 | Delete a Service Package Using deleteNetscalerServicePackage, try to delete the service package registered although there are NWs using it |  | Can this be done from Cloudstack and NCC? Does it perform the check before deleting?
10 | Failure to add NCC |  | Should give proper error message and no remnants should be left out
Install and Set up - Pre-Provisioned
11 | Install and configure NCC |  | NCC should be reachable to Cloudstack
12 | Register Cloudstack Admin keys with NCC by creating an account with NCC |  | Cloudstack account should be able to perform Admin operations in Cloudstack through NCC
13 | Add NS device to NCC | Repeat for VPX, MPX and SDX
14 | Create pre-provisioned Service Packages | VPX vs SDX vs MPX Shared vs Dedicated | 1. Service Package should be available and registered in NCC 2. listNetscalerServicePackage should list the service packages available
15 | Register NCC using registerNetscalerControlCenterAPI Provide IP, account details |  | NCC should get registered with Cloudstack listNetscalerControlCenter should list the NCC details
Network Implementation - Pre-provisioned Shared
(Tests to be run on VPX and sanity on MPX)
16 | Create Isolated Network Offering with VPX, Pre-provisioned, LB Isolation: Shared Have a Shared NS devices added through NCC |  | Should get correct drop down list of Service packages listed with NCC Network offering should get created with the service package chosen
17 | Create an account and launch Isolated network using the above offering Deploy a VM on the network |  | Guest network should get implemented and a shared NS device should get picked up from the pool of NetScalers Should bind Guest VLAN to the NS A SNIP should be acquired from Guest n/w and associated with private interface VM should be reachable to the outside world (egress should be enabled) NETWORK.OFFERING.ASSIGN, VM.CREATE, ZONE.VLAN.ASSIGN events should be generated with correct resource_id, name and type
18 | Open Egress rule and verify accessibility |  | VM should be able to access internet once Egress rule is set VR should pick up appopriate guest and public Ips
19 | Acquire public IP Create an LB rule and add the VM to the rule on port 22 - TCP |  | vserver should get created in the NS Verify that the VM is reachable on port 22 through the public IP Servers should be bind to the vserver created NET.IPASSIGN (usage), FIREWALL.OPEN events should be generated with correct resource_id, name and type
20 | Create a new LB rule with same public IP and different port - say port 80 |  | vserver should get created in the NS Verify that the VM is reachable on port 80 through the public IP Servers should be bind to the vserver created LB.CREATE - usage event
21 | Acquire another public IP Create an LB rule on same port 22 using this IP |  | vserver should get created in the NS Verify that the VM is reachable on port 22 through the public IP Servers should be bind to the vserver created
22 | Try creating another LB rule with same public IP and port |  | Should fail with suitable error message and should not have any remnants of vserver or bindings Event not generated
23 | Create a second account and launch network using the same offering Deploy VM on the network |  | Guest network should get implemented and the same shared NS device should get picked up CIDR allocated for the network should not clash with the other account's CIDR Should bind Guest VLAN to the NS A SNIP should be acquired from Guest n/w and associated with private interface VM should be reachable to the outside world (egress should be enabled) NET.IPASSIGN, VM.CREATE
24 | Acquire public IP Create an LB rule and add the VM to the rule on port 22 - TCP |  | vserver should get created in the NS Verify that the VM is reachable on port 22 through the public IP Servers should be bind to the vserver created LB.CREATE - usage event
25 | Delete the first account created |  | VM and LB rules should be removed Should remove the vserver, services, SNIP, VLAN bindings from NS VM.STOP, NETWORK.OFFERING.REMOVE, VM.DESTROY, VOLUME.DELETE, LB.DELETE, NET.IPRELEASE(for as many acquired + SourceNAT) events should be generated with the correct resource name, type and id
26 | Set capacity to a low value (3 accounts/LB rules (?)) Create that many accounts / LB rules Try to create more than the capacity |  | Should fail with appropriate error message since it's exceeded the capacity of the Shared NS
27 | Verify round robin vs leastconfigured policy for shared offering |  | Based on the policy chosen, the accounts should be allocated new device appropriately
28 | Add a secondary IP to a VM and try creating an LB rule using the secondary IP |  | Should be able to create LB rule VM should be accessible on the secondary IP through the public IP Usage for LB rule should be generated
29 | Create a VM with NICs on multiple Networks - both NS and non-NS managed networks |  | Should be able to create LB using the IP which belongs to the NS managed Network VM should be accessible on both networks Should be able to access VM on IP created with NS managed network LB rule usage should be generated for each NIC (IP) and for acquire IP as well
30 | Delete LB rules and release Public IP |  | LB rules and bindings should be cleanly removed from NS Usage should reflect removed Ips and LB Rules
31 | Perform network restart with clean up set to false |  | Post restart, LB rules should work as before
32 | Perform network restart with clean up set to true |  | Post restart, LB rules should work as before
Network Implementation - Pre-provisioned Dedicated
(Tests to be run on VPX and sanity on MPX)
33 | Create Isolated Network Offering with VPX and Pre-provisioned, Dedicated Have one Dedicated NS devices added through NCC |  | Should get correct drop down list of Service packages listed with NCC Network offering should get created with the service package chosen
34 | Create an account and launch network using the above offering Deploy a VM on the network |  | Guest network should get implemented and the NS device should get picked up from the pool of NetScalers Should bind Guest VLAN to the NS A SNIP should be acquired from Guest n/w and associated with private interface VM should be reachable to the outside work (egress should be enabled) IP usage should be generated for source NAT IP
35 | Acquire public IP Create an LB rule and add the VM to the rule on port 22 - TCP |  | vserver should get created in the NS Verify that the VM is reachable on port 22 through the public IP Servers should be bind to the vserver created IP Usage and LB Rule usage events should be generated
36 | Create a new LB rule with same public IP and different port - say port 80 |  | vserver should get created in the NS Verify that the VM is reachable on port 80 through the public IP Servers should be bind to the vserver created Usage for new IP and LB Rule usage should be generated
37 | Acquire another public IP Create an LB rule on same port 22 using this IP |  | vserver should get created in the NS Verify that the VM is reachable on port 22 through the public IP Servers should be bind to the vserver created IP Usage and LB Rule usage events should be generated
38 | Create a second account and launch network using the same offering Deploy VM on the network |  | Guest network should fail to get implemented since this is a dedicated offering and only one NS is present Verify cleanup is done properly Error message should be comprehensible Verify usage is not generated
39 | Add another Dedicated NS VPX through NCC and create a new network with the same offering Deploy a VM on the network |  | Guest network should now get implemented and the new NS device should get picked up from the pool of NetScalers Should bind Guest VLAN to the NS A SNIP should be acquired from Guest n/w and associated with private interface VM should be reachable to the outside work (egress should be enabled)
40 | Acquire public IP Create an LB rule and add the VM to the rule on port 22 - TCP |  | vserver should get created in the NS Verify that the VM is reachable on port 22 through the public IP Servers should be bind to the vserver created Usage for LB and new public IP should be generated
41 | Add a secondary IP to a VM and try creating an LB rule using the secondary IP |  | Should be able to create LB rule VM should be accessible on the secondary IP through the public IP
42 | Create a VM with NICs on multiple Networks - both NS and non-NS managed networks |  | Should be able to create LB using the IP which belongs to the NS managed Network VM should be accessible on both networks Should be able to access VM on IP created with NS managed network
43 | Delete LB rules and release Public IP |  | LB rules and bindings should be cleanly removed from NS
44 | Perform network restart with clean up set to false |  | Post restart, LB rules should work as before
45 | Verify LB functionality as external LB provider in VPC |  | Should be able to create VPC offering with NS as external LB provider (Dedicated) Should be able to create more than on LB rules with public IP Verify services and VLAN bindings are created in NS LB rule should work as expected
Network Implementation - Auto Provisioning Dedicated
46 | Create Isolated Network Offering with VPX and Auto-provisioned, Dedicated | Repeat tests on Multi POD Setup Repeat tests with Local storage enabled (and VPX sitting on local storage) Repeat tests on ZWPS | Should get correct drop down list of Service packages listed with NCC Network offering should get created with the service package chosen
47 | Create an account and launch network using the above offering Deploy a VM on the network |  | Ensure Nitro is no more called directly and all communication to NS is routed through NCC A VPX should get provisioned in Cloudstack Compute fleet while the network gets implemented NS IP should be picked up from the management CIDR Should bind Guest VLAN to the NS A SNIP should be acquired from Guest n/w and associated with private interface VM should be reachable to the outside work (egress should be enabled) VPX should be present in the Instances tab of Cloudstack (? to be decided) listNSVpx should list the VPX created
48 | IP Allocation |  | Check in DB the IP allocated to NS (SNIP and Management IP) are in allocated state and will not be picked up for anything else
49 | Acquire public IP Create an LB rule and add the VM to the rule on port 22 - TCP |  | vserver should get created in the NS Verify that the VM is reachable on port 22 through the public IP Servers should be bind to the vserver created Verify usage is generated for IP and LB
50 | Create a new LB rule with same public IP and different port - say port 80 |  | vserver should get created in the NS Verify that the VM is reachable on port 80 through the public IP Servers should be bind to the vserver created Usage for LB Rule should be generated
51 | Acquire another public IP Create an LB rule on same port 22 using this IP |  | vserver should get created in the NS Verify that the VM is reachable on port 22 through the public IP Servers should be bind to the vserver created Usage for LB Rule and public IP should be generated
52 | Create a second account and launch network using the same offering Deploy VM on the network |  | A new VPX should get provisioned in Cloudstack Compute fleet while the network gets implemented NS IP should be picked up from the management CIDR Should bind Guest VLAN to the NS A SNIP should be acquired from Guest n/w and associated with private interface VM should be reachable to the outside work (egress should be enabled) VPX should be present in the Instances tab of Cloudstack listNSVpx should list the 2 VPXs created so far
53 | Acquire public IP Create an LB rule and add the VM to the rule on port 22 - TCP |  | vserver should get created in the NS Verify that the VM is reachable on port 22 through the public IP Servers should be bind to the vserver created Usage for LB IP and public IP should be generated
54 | Add a secondary IP to a VM and try creating an LB rule using the secondary IP |  | Should be able to create LB rule VM should be accessible on the secondary IP through the public IP Usage for LB on secondary IP should be generated
55 | Create a VM with NICs on multiple Networks - both NS and non-NS managed networks |  | Should be able to create LB using the IP which belongs to the NS managed Network VM should be accessible on both networks Should be able to access VM on IP created with NS managed network
56 | Delete LB rules and release Public IP |  | LB rules and bindings should be cleanly removed from NS LB rule and IP usage should be released in usage
57 | Perform network restart with clean up set to false |  | Post restart, LB rules should work as before
58 | Perform network restart with clean up set to true |  | Post restart, LB rules should work as before VPX should be running managing the same accounts as before restart IP of NS should remain the same post restart
59 | Reserve few IPs for internal use (Use updateNetwork for reserving IPs) Create a new account with same offering and deploy VM |  | Ensure VPX is not allocated IPs from reserved range
60 | Add new set of Ips for public and management in same and different VLANs |  | Should be able to allocate IPs for VPX from new range once the old range is exhausted
61 | Release public IP after removing the LB rules |  | Should clean up the vserver and services in NS Should release usage for LB rule and IP
62 | Add a new account and fail VPX deployment (due to less capacity, no template, improper compute offering etc) |  | Should fail to implement network Network status should go back to Allocated state and get cleaned up Router deployed should get deleted IPs and VLANs allocated should get released Error message should be comprehensive as to why the deployment failed No usage should be generated
63 | Test with VPX, VMs and Router VM - all sitting in different clusters |  | Should work fine even if VPX and VMs are in different clusters
64 | Tagging compute offering of VPX |  | Should be able to add tags to compute offering
65 | Delete Network after deleting all VMs |  | All configured rules should be removed VLAN bindings, servers and services should be removed from NS
66 | Delete the account and launch a new account and network |  | Should be able to re-use the VPX for the new account All associated LB, IP, VMs should be deleted and usage released accordingly
67 | Verify VPX launch and LB on mulitple physical networks - 1. Private and public on separate networks 2. Multiple guest networks |  | Should be able to launch VPX and LB should work fine.
68 | Create VPC using NS as provider for external LB Create a tier using this vpc offering Acquire public IP and create LB rules |  | Should deploy a VPX and assign it to the VPC account Should be able to create more than on LB rules Verify services and VLAN bindings are created in NS LB rule should work as expected
69 | Create multiple VPCs with different accounts and repeat the tests |  | Should deploy a new VPX for each VPC created and LB rules should work as configured
70 | Create multiple VPCs with same accounts and repeat the tests |  | Should deploy a new VPX for each VPC Created and LB rules should work as configured
LB Services
(Tests to be executed on VPX and SDX)
72 | Created required deployment Add account and network Configure an LB rule on port 80 Add a VM to the rule | Auto Provisioned VPX SDX | LB rule should be configured and VM should be reachable using the public IP
73 | Modify the name of the LB rule |  | Should be able to modify and should reflect in the cloud DB
74 | Edit the stickiness policy of the rule |  | Should be able to update stickiness policy and should get reflected in the NS
75 | Edit the algorithm of the LB rule |  | Should be able to update LB algorithm and should get reflected in the NS
76 | Try adding and deleting VMs to/from the rule |  | Should be able to add/remove VMs and should get reflected in the NS
77 | Verify LB rules sanity on mulitple physical networks - 1. Private and public on separate networks 2. Multiple guest networks |  | Should be able to create LB rules appropriately and should work fine.
AutoScale:
78 | Verify autoscaling with scale up and down on CPU Verify both scale up and scale down conditions Verify with different values of min and max | Test on both shared and dedicated offerings | Autoscaling should work as expected
79 | Verify autoscaling with scale up and down on Response time Verify both scale up and scale down conditions Verify with different values of min and max
80 | Re-generate API and Secret Keys and verify autoscaling again |  | Autoscaling should work as expected after disabling/enabling it back for updating the keys
81 | Verify autoscaling with multiple accounts and networks |  | Autoscaling should work as expected as per shared/dedication policy
82 | Test autoscaling with User data passed into the config |  | Autoscaled VMs should have userdata incorporated in every VM
83 | Delete an accounts which has autoscaling policies configured |  | Account and network should get cleaned up completely All VMs, rules, vservers, bindings, dns records should get deleted from Cloudstack/NS
84 | Live Migrate Autoscaled VMs |  | Should be able to live migrate VMs without any impact on the LB rules
85 | Reboot Autoscaled VMs |  | Should be able to restart VMs without any impact on the LB rules
86 | Restart a network which has Autoscale rules with cleanup set to false |  | Should be able to restart without any impact on the LB rules
87 | Restart a network which has Autoscale rules with cleanup set to true |  | Should re-configure all rules and should not have any impact on the LB rules
Health Checks
88 | Should be able to configure and report health check for LB rules |  | Health check results should be appropriately reported based on the status of the services chosen
89 | Bring down one of the VMs and verify status |  | Health check should indicate that the service is down
90 | Add more VMs to the LB rule |  | Health check should indicate status of the new VM service
91 | Bring back the VM which went down |  | Health check status should be appropriately reflected
SDX
92 | Add SDX device through NCC Create Isolated Network Offering in Cloudstack with SDX service package and Auto-provisioned, Dedicated | Repeat sanity tests on Multi POD Setup and 2 SDX devices in same and different POD | Should get correct drop down list of Service packages listed with NCC Network offering should get created with the service package chosen
93 | Create an account and launch network using the above offering Deploy a VM on the network |  | Ensure Nitro is no more called directly and all communication to NS is routed through NCC The POD CIDR should get identified and sent by NCC to Cloudstack through acquire_pod_network_ip A VPX should get provisioned in SDX using this CIDR Should bind Guest VLAN to the NS A SNIP should be acquired from Guest n/w and associated with private interface Network should get implemented VM should be reachable to the outside work (egress should be enabled) VPX should be present in the Instances tab of Cloudstack listNSVpx should list the VPX created
94 | IP Allocation |  | Check in DB the IP allocated to NS (SNIP and Management IP) are in allocated state and will not be picked up for anything else
95 | Acquire public IP Create an LB rule and add the VM to the rule on port 22 - TCP |  | vserver should get created in the NS Verify that the VM is reachable on port 22 through the public IP Servers should be bind to the vserver created Usage for LB and IP should be generated
96 | Create a new LB rule with same public IP and different port - say port 80 |  | vserver should get created in the NS Verify that the VM is reachable on port 80 through the public IP Servers should be bind to the vserver created Usage for public IP and LB rule
97 | Acquire another public IP Create an LB rule on same port 22 using this IP |  | vserver should get created in the NS Verify that the VM is reachable on port 22 through the public IP Servers should be bind to the vserver created Usage for LB and IP should be generated
98 | Create a second account and launch network using the same offering Deploy VM on the network |  | CIDR should be derived by NCC again and passed appropriately to Cloudstack A new VPX should get provisioned in SDX using this CIDR Should bind Guest VLAN to the NS A SNIP should be acquired from Guest n/w and associated with private interface Network should get implemented VM should be reachable to the outside work (egress should be enabled) VPX should be present in the Instances tab of Cloudstack listNSVpx should list the 2 VPXs created so far
99 | Acquire public IP Create an LB rule and add the VM to the rule on port 22 - TCP |  | vserver should get created in the NS Verify that the VM is reachable on port 22 through the public IP Servers should be bind to the vserver created Usage for LB and IP should be generated
100 | Set capacity to a low value (3 accounts/LB rules (?)) Create that many accounts / LB rules Try to create more than the capacity |  | Should fail with appropriate error message since it's exceeded the capacity of the Shared NS
101 | Add a secondary IP to a VM and try creating an LB rule using the secondary IP |  | Should be able to create LB rule VM should be accessible on the secondary IP through the public IP Usage on secondary IP should be generated
102 | Create a VM with NICs on multiple Networks - both NS and non-NS managed networks |  | Should be able to create LB using the IP which belongs to the NS managed Network VM should be accessible on both networks Should be able to access VM on IP created with NS managed network Usage on each IP in every NIC should be generated along with LB.RULE
103 | Delete LB rules and release Public IP |  | LB rules and bindings should be cleanly removed from NS
104 | Perform network restart with clean up set to false |  | Post restart, LB rules should work as before
105 | Perform network restart with clean up set to true |  | Post restart, LB rules should work as before VPX should be running managing the same accounts as before restart IP of NS should remain the same post restart
106 | Reserve few IPs for internal use (Use updateNetwork for reserving IPs) Create a new account with same offering and deploy VM |  | Ensure VPX is not allocated IPs from reserved range
107 | Add new set of Ips for public and management in same and different VLANs |  | Should be able to allocate IPs for VPX from new range once the old range is exhausted
108 | Release public IP after removing the LB rules |  | Should clean up the vserver and services in NS
109 | Add a new account and fail VPX deployment (due to less capacity, no template, improper compute offering etc) |  | Should fail to implement network Network status should go back to Allocated state and get cleaned up Router deployed should get deleted IPs and VLANs allocated should get released Error message should be comprehensive as to why the deployment failed
110 | Test with VPX, VMs and Router VM - all sitting in different clusters |  | Should work fine even if VPX and VMs are in different clusters
111 | Tagging compute offering of VPX?
112 | Delete Network after deleting all VMs |  | All configured rules should be removed VLAN bindings, servers and services should be removed from NS
113 | Delete the account and launch a new account and network |  | Should be able to re-use the VPX for the new account
114 | Verify VPX launch and LB on mulitple physical networks - 1. Private and public on separate networks 2. Multiple guest networks |  | Should be able to launch VPX and LB should work fine.
115 | Create VPC using NS as provider for external LB Create a tier using this vpc offering Acquire public IP and create LB rules |  | Should deploy a VPX and assign it to the VPC account Should be able to create more than on LB rules Verify services and VLAN bindings are created in NS LB rule should work as expected
116 | Create multiple VPCs with different accounts and repeat the tests |  | Should deploy a new VPX for each VPC created and LB rules should work as configured
117 | Create multiple VPCs with same accounts and repeat the tests |  | Should deploy a new VPX for each VPC (?)created and LB rules should work as configured - not sure if it is each VPC
HA and Failover
118 | Create offering with HA enabled with VPX Use this offering to create Network Launch a VM in this network |  | Should deploy 2 VPX in different clusters and should be paired and set in active-passive mode Verify this in NCC
119 | Bring down the active VPX manually |  | Should failover to the redundant VPX Should not impact LB traffic Should be able to identify from NCC which one is down Should be able to bring up the VPX which went down Verify LB services are active
120 | Bring down the active VPX manually by making the host go down |  | Should failover to the redundant VPX Should not impact LB traffic Should be able to identify from NCC which one is down Should be able to bring up the VPX which went down in another host Verify LB services are active
121 | Create a zone with multiple PODs and one SDX in each POD Create offering with HA enabled and with SDX Use this offering to create Network Launch a VM in this network |  | Fail ? Since the SDXs are in different PODs or should the VPXs be deployed in the same POD
122 | Create a zone with multiple PODs and both SDX in same POD Create offering with HA enabled and with SDX Use this offering to create Network Launch a VM in this network |  | Behaviour in this case?
| One of the VPX pair fails deploying |  | Network implement fails with appopriate error message Already launched VPX will be either destroyed or will be re-used for the next deployment
Upgrade
123 | Upgrade a non-NS (VR) managed NW to an NCC managed network Choose auto provisioned offering |  | Should be able to edit the offering for the network VMs expected to be down in this case VPX should be deployed in compute fleet All LB rules re-configured to the VPX
124 | Create a pre-hollywood set up with NS managed networks Create Autoscaled LB rules Upgrade to Hollywood Bring down VMs of the network and add the same VPX to NCC Upgrade network offerings to use pre-provisioned VPX |  | Should be able to edit the offering for the network VMs expected to be down during the upgrade A VPX from the pre-provisioned fleet should be picked up The network should get re-implemented and there should be no conflicts in terms of VLANs or Ips All LB rules should be re-configured to the new VPX
125 | Create a pre-hollywood set up with NS managed networks Create Autoscaled LB rules Upgrade to Hollywood Upgrade network offerings to use auto-provisioned VPX |  | Should be able to edit the offering for the network VMs expected to be down during the upgrade A new VPX should be provisioned in compute fleet The network should get re-implemented and there should be no conflicts in terms of VLANs or Ips All LB rules should be re-configured to the new VPX
126 | Create a pre-hollywood set up with SDX managed networks Create Autoscaled LB rules Upgrade to Hollywood Upgrade network offerings to use SDX (with NCC) |  | Should be able to edit the offering for the network VMs expected to be down during the upgrade New VPX will be provisioned in the same SDX (or whichever is avaiable) The network should get re-implemented and there should be no conflicts in terms of VLANs or Ips All LB rules should be re-configured to the new VPX
127 | Create a pre-hollywood set up with an MPX managed networks Upgrade to Hollywood Bring down VMs of the network and add the same MPX to NCC Upgrade network offerings to use pre-provisioned MPX |  | Should be able to edit the offering for the network VMs expected to be down during the upgrade MPX from the pre-provisioned fleet should be picked up The network should get re-implemented and there should be no conflicts in terms of VLANs or Ips All LB rules should be re-configured to the new VPX
128 | Upgrade from NCC managed VPX to SDX |  | ?
129 | Upgrade from NCC managed MPX to VPX |  | ?
Combinations of offerings / Failure cases / Miscellaneous
130 | Create multiple offerings - VPX, SDX, shared, Dedicated, Pre-provisioned and auto-provisioned and combinations of these Create suitable network offerings for few of these Launch network and VMs |  | Verify that the correct offering is chosen and the appropriate device is used as per the provisioning specified while implementing the network
131 | Repeat for multiple accounts |  | Verify that the correct offering is chosen and the appropriate device is used as per the provisioning specified while implementing the network
132 | Multiple zones with ESXi and XS Perform Sanity tests with different devices and configurations |  | Does NCC understand the concept of mulitple zones? Verify that two different images are made avaiable for the two zone for different hypervisors Should pick up appropriate image while deploying VPX Verify LB rules and other basic functionalities
133 | Delete a NS from NCC/Cloudstack which is currently in use |  | Should be able to restart the network and the LB rules should get transferred to the new device - test with auto provisioned and pre-provisioned
134 | Modify the compute offering of VPX to use tags |  | Should be able to deploy VPX with the new compute offering (system offering) and use the appropriate tag In case no hosts with that tag should it fail?
135 | Regenerate API keys in Cloudstack for the acccount registered with NCC |  | NCC should pick up new API keys Auto provisioning and LB rules should work fine with new keys
136 | Perform sanity tests with Clustered MS Setup for auto provisioning and SDX |  | Auto provisioning and LB rules should work fine on clustered MS Setup LB rules and accessibility should work as expected
137 | Make a VPX temporarily unavailable (without HA) and bring it up back online again |  | LB rules will not function for that time and then is back up once NS is up again
GSLB
138 | Add NS device through NCC and check GSLB to be true Create a set of LB rules across zones Assign these rules using assignToGSLBRule | Repeat on SDX and auto provisioned VPX | LB rules should get assigned to the GSLB rule Verify accessibility
139 | Verify with multiple physical networks |  | LB rules should get assigned to the GSLB rule Verify accessibility
140 | Removing Rules, editing and adding new rules
141 | Account and network deletions
142 | List Rules
Multiple physical networks
| private and public on separate n/w: Supported with pre-provisioned dedicated | Should configure service pkgs with dedicated NS added
| private and public on separate n/w: Supported with pre-provisioned shared | Should configure service pkgs with shared NS added
| Multiple guest networks - pre provisioned | Not sure if this will work - need to test - should add NS such that the offering is tied to the appropriate service package to which the NS is added
| Multiple guest networks - auto provisioned | Not supported

## Sheet2
Repeat tests with multiple secondary storages
Multiple PODs
One secondary goes full and a new one is added - test VPX launch
Ability to deploy NS in separate cluster
If 2 SDX are in separate PODs and we try to deploy HA enabled NS, will this fail since it is recommended to have VPX pairs to be deployed in same POD